## Sheet1
Shipment_No | Customer_Name | Sales_Person | Job_Owner | Container_Types | HBL_No / BL_No | Cargo_Type | Loading_Port | Place_of_Delivery | SI_Submission_Actual | SI_Submission_Planned | Container_Stuffing_Actual | Container_Stuffing_Planned | Gate_in_Confirmation_Actual | Gate_in_Confirmation_Planned | On_Board_Confirmation_Actual | On_Board_Confirmation_Planned | Line_Invoice_Received_Actual | Line_Invoice_Received_Planned | Operational_Job_Lock_Actual | Operational_Job_Lock_Planned | Tax_Invoice_to_Client_Actual | Tax_Invoice_to_Client_Planned | Line_Invoice_Payment_Actual | Line_Invoice_Payment_Planned | HBL_and_MBL_release_Actual | HBL_and_MBL_release_Planned | Docs_Sent_to_customer_Actual | Docs_Sent_to_customer_Planned | Pre_Alert_Actual | Pre_Alert_Planned | Remarks
SHP/SE/0015/25-26 | MAGNUM LUBRICANTS (INDIA) PVT LTD | Ganesh Gatate | Bipin | 1x40HC | MAEU | FCL | (INNSA) Nhava Sheva | (AEJEA) Jebel Ali | 2025-04-10 |  | 2025-04-10 |  | 2025-04-10 |  | 2025-04-10 |  | 2025-04-10 |  | 2025-04-10 | 2025-04-10
SHP/SE/0045/25-26 | FAIRMACS SHIPPING AND TRANSPORT SERVICES PRIVATE LIMITED | AARON ALBERT RAJ | Jagan Pillai | 1x20GP | ASCLPTLSHJ2500001 | FCL | (INMUN) Mundra | (AESHJ) Sharjah | 2025-04-05 |  | 2025-04-04 |  | 2025-04-11 |  | 2025-04-14 |  | 2025-04-14 |  | 2025-04-15 | 2025-04-15 | 2025-04-15 |  | 2025-04-15
SHP/SE/0304/25-26 | BIOSTADT INDIA LIMITED | Siddharth Oberoi | Bipin | 1x20GP | ISAMUM0660 / OOLU8899190060 | FCL | (INNSA) Nhava Sheva | (VNVIC) Ho Chi Minh, VICT | 2025-06-27 | 2025-06-26 | 2025-06-25 | 2025-06-25 | 2025-07-02 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-08 |  | 2025-07-08 |  |  |  | 2025-07-08
SHP/SE/0306/25-26 | 3Q PRINTING TECHNOLOGIES PRIVATE LIMITED | Anup Ramdas | Bipin | 1x40HC | ISAMUM0663 / HDMUBOMM06782200 | FCL | (INNSA) NHAVA SHEVA, INDIA | (USBAL) BALTIMORE, USA | 2025-06-27 |  | 2025-06-27 |  | 2025-06-28 |  | 2025-07-02 |  | 2025-07-03 |  | 2025-07-15 | 2025-07-15 |  | 2025-07-20 |  | 2025-07-08 |  | 2025-07-08 |  |  |  |  | DT.10.07.2025 - PRE-ALERT ACK BY AGENT DT.15.07.2025 - AWAITING TAX INVOCIE APPROVAL FROM SHIPPER
SHP/SE/0346/25-26 | M/S.EXQUISITE RUGS | Jagan Pillai | Sameer Ramesh Thakare | 1x40HC | ISAMUM0677 / COSU6423546490 | FCL | (INNSA) Nhava Sheva | (USLAX) Los Angeles | 2025-07-11 | 2025-07-07 | 2025-07-05 | 2025-07-05 | 2025-07-10 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-17 | 2025-07-19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-07-19 | 2025-07-18 | 2025-07-21 |  |  |  | 2025-07-22 | DT.17.07.2025 - INVOICE/ON BOARD RECEIVED, BILL TO ALL FIVE SHIPPER PENDING/DT.16.07.2025 - HBL AND MBL AMS DETAILS FORWADED TO AGENT/DT.15.07.2025 - AWAITING CONSOLE HOUSE AMS AND SHIPMNET PLAN TO SAILED ON 16.07.2025
SHP/SE/0502/25-26 | ATLAS WORLDWIDE LOGISTICS | Anup Ramdas | Shubhangi | 1x40HC | ISAMUM0726 / COSU6427491190 | FCL | (INMUN) Mundra | (USLAX) Los Angeles | 2025-08-26 | 2025-08-22 | 2025-08-19 | 2025-08-19 | 2025-08-30 | 2025-08-26 | 2025-08-31 | 2025-08-29 | 2025-09-01 | 2025-08-29 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-08-29 | 2025-09-03 | 2025-08-29 |  | 2025-09-15 |  |  |  | 2025-09-15
SHP/SE/0523/25-26 | GOEL EXPORTS | Anup Ramdas | Shubhangi | 1x40HC | ISAMUM0733 / COSU6427491190 | FCL | (INMUN) Mundra | (USLAX) Los Angeles | 2025-08-20 | 2025-08-20 | 2025-08-19 | 2025-08-19 | 2025-08-30 | 2025-08-27 | 2025-08-31 | 2025-08-29 | 2025-08-31 | 2025-08-29 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-08-29 | 2025-09-03 | 2025-08-29 |  | 2025-09-15 |  |  |  | 2025-09-15
SHP/SE/0548/25-26 | ATLAS WORLDWIDE LOGISTICS | Anup Ramdas | Shubhangi | 1x40HC | ISAMUM0744 / COSU6428959650 | FCL | (INMUN) Mundra | (USCGQ) Columbus Grove | 2025-09-05 | 2025-09-06 | 2025-09-05 | 2025-09-06 | 2025-09-15 | 2025-09-15 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-09-18 |  |  |  | 2025-09-18
SHP/SE/0549/25-26 | JAYANT AGRO ORGANICS LTD | Anup Ramdas | Shubhangi | 1x20GP | ISAMUM0745 / TRLMUNCGP917729 | FCL | (INMUN) Mundra | (BDCGP) Chittagong | 2025-09-09 | 2025-09-09 | 2025-09-08 | 2025-09-08 | 2025-09-12 | 2025-09-11 |  | 2025-09-19 |  | 2025-09-19 |  |  |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-19 |  |  |  | 2025-09-19 | REvaildate booking send
SHP/SE/0550/25-26 | JAYANT AGRO ORGANICS LTD | Anup Ramdas | Shubhangi | 1x20GP | ISAMUM0746 / HDMU | FCL | (INMUN) Mundra | (BDCGP) Chittagong | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-06 | 2025-09-13 | 2025-09-13 |  | 2025-09-19 |  | 2025-09-19 |  |  |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-20 |  |  |  | 2025-09-20
SHP/SE/0557/25-26 | JEENA & COMPANY | Ganesh Gatate | Santosh Hulvale | 2x40HC | BOM500337900 | FCL | (INNSA) Nhava Sheva | (EGSOK) Sokhna Port | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-08 | 2025-09-07 | 2025-09-10 | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-10 | 2025-09-13 | 2025-09-11 |  | 2025-09-15 |  |  |  | 2025-09-15 | 14/09 OBL RELEASE ON 15/09 //09/09-WAITING SOB CONFIRMATION
SHP/SE/0565/25-26 | INTERCARE SERVICES LTD. | Anup Ramdas | Shubhangi | 1x20GP | ISAMUM0749 | FCL | (INMAA) Chennai (ex Madras) | (BDCGP) Chittagong | 2025-09-11 | 2025-09-10 | 2025-09-11 | 2025-09-10 | 2025-09-13 | 2025-09-12 | 2025-09-18 | 2025-09-18 |  | 2025-09-19 |  |  |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-19 |  |  |  | 2025-09-19
SHP/SE/0566/25-26 | NAVICOM CORPORATION | Ashritha Rai | Sameer Ramesh Thakare |  | 61BOM0024130 | LCL | (INNSA) Nhava Sheva | (SADMM) Ad Dammam | 2025-09-12 | 2025-09-10 |  | 2025-09-13 |  | 2025-09-13 |  | 2025-09-14 |  | 2025-09-13 |  |  |  | 2025-09-13 |  | 2025-09-13 |  | 2025-09-13 |  |  |  |  | 14/09 - AWAITING STUFFING CONFIRMATION, GATE IN , ON NBOARD CONFIRMATION FROM FM GLOBAL/ 12/09 - PLANNING STUFFING TODAY OR TOMORROW - AFTER PALLETISTION WORK OUT /CARGO CARTED ON 11/09
SHP/SE/0567/25-26 | JKP MICROMINERALS INDIA PRIVATE LIMITED | Anup Ramdas | Shubhangi | 1x20GP | TRLNSASIN8026120 | FCL | (INNSA) Nhava Sheva | (SGSIN) Singapore | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-15 | 2025-09-15 | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-09-18 |  |  |  | 2025-09-18
SHP/SE/0568/25-26 | YOKOHAMA INDIA PRIVATE LIMITED | AARON ALBERT RAJ | Santosh Hulvale | 1x40HC | ISAMUM0750 / ACB0156738 | FCL | (INMUN) MUNDRA, INDIA | (NZAKL) AUCKLAND, NEW ZEALAND | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-12 | 2025-09-11 | 2025-09-14 | 2025-09-12 | 2025-09-15 | 2025-09-12 |  |  |  | 2025-09-16 |  | 2025-09-16 |  | 2025-09-16 |  |  |  | 2025-09-16
SHP/SE/0572/25-26 | VEA IMPEX (I) PRIVATE LIMITED | Royston Dsouza | Sameer Ramesh Thakare | 1x20GP | MAEU259306237 | FCL | (INMUN) Mundra | (GHTEM) Tema | 2025-09-12 | 2025-09-12 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-15 | 2025-09-16 |  | 2025-09-17 |  |  |  | 2025-09-17 | 14-09- SHPT VSL SAILED IN 15/09 -0830 HRS//CONTAINER PLANNING FOR STUFFING ON 11/09
SHP/SE/0573/25-26 | WANBURY LIMITED | Vikrant Vakhare | Santosh Hulvale |  |  | LCL | (INNSA) Nhava Sheva | (ARBUE) Buenos Aires | 2025-09-15 | 2025-09-15 |  | 2025-09-27 |  | 2025-09-29 |  | 2025-10-01 |  | 2025-10-02 |  |  |  | 2025-10-02 |  | 2025-10-03 |  | 2025-10-03 |  |  |  | 2025-10-03 | LCL -
SHP/SE/0578/25-26 | WANBURY LIMITED | Vikrant Vakhare | Santosh Hulvale | 1x20GP | A32FX12723 | FCL | (INNSA) Nhava Sheva | (TWKEL) Keelung (Chilung) | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-14 | 2025-09-13 | 2025-09-15 | 2025-09-13 | 2025-09-15 | 2025-09-15 |  | 2025-09-16 |  | 2025-09-16 |  | 2025-09-16 |  |  |  | 2025-09-16
SHP/SE/0580/25-26 | M/S.EXQUISITE RUGS | Jagan Pillai | Sameer Ramesh Thakare | 1x20GP, 3x40HC | ISAMUM0753 / COSU6429108370 | FCL | (INNSA) Nhava Sheva | (USNYC) New York | 2025-09-10 |  | 2025-09-10 | 2025-09-09 | 2025-09-12 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-09-20 |  |  |  | 2025-09-20 | AMS FOLLOW WITH COSCO AND SEND AMS DETAILS FOR FILING ISF TODAY
SHP/SE/0581/25-26 | AKASH EXPORTS | Siddharth Oberoi | Santosh Hulvale | 1x40HC | WS2503100460 | FCL | (INNSA) Nhava Sheva | (SAJED) Jeddah | 2025-09-14 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-16 | 2025-09-14 | 2025-09-18 | 2025-09-17 | 2025-09-18 | 2025-09-17 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-19 |  |  |  | 2025-09-19 | CONTAINER UNDER STUFFING
SHP/SE/0582/25-26 | COHIZON LIFE SCIENCES LIMITED | Mithilesh Shetty | Shubhangi | 1x20GP | ONEYMUMF84723600 | FCL | (INNSA) Nhava Sheva | (GBSOU) Southampton | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-09-18 |  |  |  | 2025-09-18
SHP/SE/0583/25-26 | JEENA & COMPANY | Ganesh Gatate | Sameer Ramesh Thakare | 1x40HC | BOM500337901 | FCL | (INNSA) Nhava Sheva | (EGSOK) Sokhna Port | 2025-09-06 | 2025-09-05 | 2025-09-05 | 2025-09-04 | 2025-09-06 | 2025-09-05 | 2025-09-10 | 2025-09-10 | 2025-09-12 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-11 | 2025-09-12 | 2025-09-11 |  | 2025-09-15 |  |  |  | 2025-09-15 | 14/09- OBL RELEASED ON 15/09
SHP/SE/0586/25-26 | REICHHOLD INDIA PRIVATE LIMITED | Santosh Shetty | Sameer Ramesh Thakare | 1x20GP | AMC2440939 | FCL | (INNSA) Nhava Sheva | (SOMGQ) Mogadishu | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | [10 empty] | CONTAINER PLANNING TO GATE 12/09 TONIGHT
SHP/SE/0587/25-26 | WANBURY LIMITED | Vikrant Vakhare | Santosh Hulvale | 1x40HC | COSU8035164790 | FCL | (INNSA) Nhava Sheva | (VNSGN) Ho Chi Minh City | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-13 | 2025-09-13 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-17 |  | 2025-09-17 |  |  |  | 2025-09-17 | 12-09-CONTAINER UNDER STUFFING
SHP/SE/0589/25-26 | YOKOHAMA INDIA PRIVATE LIMITED | AARON ALBERT RAJ | Santosh Hulvale | 3x40HC | MEDUKD551496 | FCL | (INMUN) Mundra | (MACAS) Casablanca | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-17 | 2025-09-17 |  | 2025-09-26 |  | 2025-09-27 |  |  |  | 2025-09-27 |  | 2025-09-27 |  | 2025-09-29 |  |  |  | 2025-09-29
SHP/SE/0591/25-26 | REAGENS INDIA POLYMER ADDITIVES PRIVATE LIMITED | Deepak Palande | Sameer Ramesh Thakare | 2x40HC | ONEYBRDF09099400 | FCL | (INHZA) Hazira Port/Surat | (ZADUR) Durban | 2025-09-14 | 2025-09-14 | 2025-09-13 | 2025-09-13 | 2025-09-14 | 2025-09-14 |  | 2025-09-18 |  | 2025-09-19 |  |  |  | 2025-09-19 |  | 2025-09-20 |  | 2025-09-20 |  |  |  | 2025-09-22 | 15/09 - 1ST APPROVAL PENDING //14/09 1ST PRINT FOLLOW UP /SI SUBMITTED //13/09 - STUFFING ON TODAY SI SUBMISSOIN TOMORROW
SHP/SE/0592/25-26 | ALPHA CHEMIKA | Ashritha Rai | Shubhangi | 1x40HC | MAEU | FCL | (INNSA) Nhava Sheva | (SNDKR) Dakar |  | 2025-10-04 |  | 2025-10-03 |  | 2025-10-08 |  | 2025-10-10 |  | 2025-10-10 |  |  |  | 2025-10-10 |  | 2025-10-10 |  | 2025-10-10 |  |  |  | 2025-10-10
SHP/SE/0593/25-26 | BIOSTADT INDIA LIMITED | Siddharth Oberoi | Santosh Hulvale | 1x20GP | OOLU2312009000 | FCL | (INNSA) Nhava Sheva | (IDSUB) Surabaya | 2025-09-16 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-17 | 2025-09-17 |  | 2025-09-19 |  | 2025-09-19 |  |  |  | 2025-09-20 |  | 2025-09-20 |  | 2025-09-22 |  |  |  | 2025-09-22
SHP/SE/0594/25-26 | SPECTRUM FOOD PRODUCTS | Siddharth Oberoi | Santosh Hulvale | 2x40HC | HLCUBO12509ARPI0 | FCL | (INNSA) Nhava Sheva | (MAPTM) Tanger Med | 2025-09-17 | 2025-09-17 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-17 |  | 2025-09-21 |  | 2025-09-22 |  |  |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-23 |  |  |  | 2025-09-23
SHP/SE/0595/25-26 | SPECTRUM FOOD PRODUCTS | Siddharth Oberoi | Santosh Hulvale | 1x40HC | 259318450 | FCL | (INNSA) Nhava Sheva | (ITLIV) Livorno | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-18 | 2025-09-18 |  | 2025-09-21 |  | 2025-09-22 |  |  |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-23 |  |  |  | 2025-09-23
SHP/SE/0596/25-26 | INTERCARE SERVICES LTD. | Anup Ramdas | Shubhangi | 1x20GP | ISAMUM0754 | FCL | (INMAA) Chennai (ex Madras) | (BDCGP) Chittagong | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-21 |  | 2025-09-23 |  | 2025-09-23 |  |  |  | 2025-09-23 |  | 2025-09-23 |  | 2025-09-23 |  |  |  | 2025-09-23
SHP/SE/0597/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Shubhangi |  |  | LCL | (INNSA) Nhava Sheva | (BDCGP) Chittagong | 2025-09-17 | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-09-19 |  | 2025-09-20 |  | 2025-09-20 |  |  |  | 2025-09-22 |  | 2025-09-20 |  | 2025-09-20
SHP/SE/0598/25-26 | ASIAN TIRE FACTORY LIMITED | AARON ALBERT RAJ | Sameer Ramesh Thakare | 1x40HC | CMDU AMC2440259 | FCL | (INMUN) Mundra | (SADMM) Ad Dammam | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-16 |  | 2025-09-25 |  | 2025-09-30 |  | 2025-10-01 |  |  |  | 2025-10-01 |  | 2025-10-01 |  | 2025-10-02 |  |  |  | 2025-10-04 | 17/09- REVISED BOOKING PLACED
SHP/SE/0599/25-26 | ASIAN GLOBAL EXPORTS | Roopesh Suvarna | Sameer Ramesh Thakare | 1x40HC | CMDU | FCL | (INMUN) Mundra | (JOAQB) 'Aqaba |  | 2025-09-23 |  | 2025-09-20 |  | 2025-09-26 |  | 2025-09-29 |  | 2025-09-30 |  |  |  | 2025-09-30 |  | 2025-09-30 |  | 2025-09-30 |  |  |  | 2025-10-01 | 17/09 - BOOKING REVALIDATE TILL 19/09
SHP/SE/0600/25-26 | AKASH EXPORTS | Siddharth Oberoi | Sameer Ramesh Thakare | 1x40HC | MAEU258651575 | FCL | (INNSA) Nhava Sheva | (KWSWK) Shuwaikh |  | 2025-09-20 |  | 2025-09-19 |  | 2025-09-23 |  | 2025-09-25 |  | 2025-09-26 |  |  |  | 2025-09-27 |  | 2025-09-27 |  | 2025-09-27 |  |  |  | 2025-09-29 | CONTAINER STUFFING PLANNING ON 19/09
SHP/SE/0601/25-26 | MAGNUM LUBRICANTS (INDIA) PVT LTD | Ganesh Gatate | Sameer Ramesh Thakare | 1x20GP | AMC2443838 | FCL | (INNSA) Nhava Sheva | (LBBEY) Beirut |  | 2025-09-27 |  | 2025-09-17 |  | 2025-09-29 |  | 2025-10-02 |  | 2025-10-03 |  |  |  | 2025-10-03 |  | 2025-10-03 |  | 2025-10-04 |  |  |  | 2025-10-06 | 17/09 - booking rollover request on vsl : CMA CGM BUTTERFLY v: 0MXO2W1MA
SHP/SE/0602/25-26 | JEENA & COMPANY | Ganesh Gatate | Shubhangi | 1x20GP |  | FCL | (INNSA) Nhava Sheva | (TZZNZ) Zanzibar |  | 2025-09-18 |  | 2025-09-18 |  | 2025-09-20 |  | 2025-09-22 |  | 2025-09-22 |  |  |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-23 |  |  |  | 2025-09-23
SHP/SE/0603/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Shubhangi |  |  | LCL | (INNSA) Nhava Sheva | (BDCGP) Chittagong | 2025-09-18 | 2025-09-17 | 2025-09-16 | 2025-09-16 |  | 2025-09-22 |  | 2025-09-24 |  | 2025-09-24 |  |  |  | 2025-09-24 |  | 2025-09-24 |  | 2025-09-25 |  |  |  | 2025-09-25
SHP/SE/0604/25-26 | ATLAS WORLDWIDE LOGISTICS | Anup Ramdas | Shubhangi | 1x40HC | ISAMUM0755 / COSU | FCL | (INNSA) Nhava Sheva | (USCHI) Chicago |  | 2025-09-23 |  | 2025-09-23 |  | 2025-09-23 |  | 2025-09-28 |  | 2025-09-28 |  |  |  | 2025-09-29 |  | 2025-09-29 |  | 2025-09-29 |  |  |  | 2025-09-29
SHP/SE/0605/25-26 | BIOSTADT INDIA LIMITED | Siddharth Oberoi | Sameer Ramesh Thakare | 1x20GP | ISAMUM0756 / ONEYMUMF86769400 | FCL | (INNSA) NHAVA SHEVA, INDIA | (VNSGN) HO CHI MINH (CAT LAI) | 2025-09-18 | 2025-09-18 |  | 2025-09-19 |  | 2025-09-20 |  | 2025-09-23 |  | 2025-09-24 |  |  |  | 2025-09-24 |  | 2025-09-25 |  | 2025-09-25 |  |  |  | 2025-09-26 | 17/09 - stuffing planning on 18/09 as container Gate Opening on 20/09
SHP/SE/0606/25-26 | JEENA & COMPANY | Ganesh Gatate | Sameer Ramesh Thakare | 2x40HC | MAEU | FCL | (INNSA) Nhava Sheva | (LYBEN) Bingazi (Benghazi) |  | 2025-10-08 |  | 2025-10-08 |  | 2025-10-10 |  | 2025-10-12 |  | 2025-10-13 |  |  |  | 2025-10-14 |  | 2025-10-14 |  | 2025-10-14 |  |  |  | 2025-10-15 | YET TO CONFIRM STUFFING DATE BY CUSTOMER
SHP/SE/0607/25-26 | SOLWING IMPEX LLP | Siddharth Oberoi | Shubhangi |  |  | LCL | (INNSA) Nhava Sheva | (IDSRG) Semarang |  | 2025-09-18 |  | 2025-09-18 |  | 2025-09-22 |  | 2025-09-22 |  | 2025-09-22 |  |  |  | 2025-09-23 |  | 2025-09-23 |  | 2025-09-23 |  |  |  | 2025-09-23
SHP/SE/0608/25-26 | WANBURY LIMITED | Vikrant Vakhare | Santosh Hulvale |  |  | LCL | (INNSA) Nhava Sheva | (EGALY) El Iskandariya (Alexandria) |  | 2025-09-22 |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-25 |  | 2025-09-26 |  |  |  | 2025-09-26 |  | 2025-09-27 |  | 2025-09-27 |  |  |  | 2025-09-27
SHP/SE/0609/25-26 | Falcon 18 Imports Pvt. Ltd. | Ganesh Gatate | Sameer Ramesh Thakare | 1x40HC | MAEU | FCL | (INMUN) Mundra | (SOMGQ) Mogadishu |  | 2025-09-27 |  | 2025-09-26 |  | 2025-09-29 |  | 2025-10-01 |  | 2025-10-03 |  |  |  | 2025-10-03 |  | 2025-10-03 |  | 2025-10-03 |  |  |  | 2025-10-04
SHP/SE/0610/25-26 | WANBURY LIMITED | Vikrant Vakhare | Shubhangi | 1x40RF |  | FCL | (INKTP) Kattupalli Port | (JOAQB) 'Aqaba |  | 2025-09-20 |  | 2025-09-20 |  | 2025-09-26 |  | 2025-09-28 |  | 2025-09-28 |  |  |  | 2025-09-29 |  | 2025-09-29 |  | 2025-09-30 |  |  |  | 2025-09-30
SHP/SE/0611/25-26 | BARCO SHIPPING PRIVATE LIMITED | Siddharth Oberoi | Sameer Ramesh Thakare | 1x40OT |  | FCL | (INNSA) Nhava Sheva | (SGSIN) Singapore |  | 2025-09-24 |  | 2025-09-22 |  | 2025-09-24 |  | 2025-09-26 |  | 2025-09-29 |  |  |  | 2025-09-29 |  | 2025-09-29 |  | 2025-09-30 |  |  |  | 2025-09-30
SHP/SE/0612/25-26 | BARCO SHIPPING PRIVATE LIMITED | Siddharth Oberoi | Sameer Ramesh Thakare | 1x40OT |  | FCL | (INNSA) Nhava Sheva | (SGSIN) Singapore |  | 2025-09-23 |  | 2025-09-22 |  | 2025-09-24 |  | 2025-09-26 |  | 2025-09-29 |  |  |  | 2025-09-29 |  | 2025-09-29 |  | 2025-09-30 |  |  |  | 2025-11-01