## Sheet1
Shipment_No | Customer_Name | Sales_Person | Job_Owner | Container_Types | HBL_No / BL_No | Cargo_Type | Origin | Destination | Shipment_Date | ETA Actual | ETA Planned | ETD Actual | ETD Planned | Quotation Actual | Quotation Planned | Booking Actual | Booking Planned | HBL & MBL Draft_Actual | HBL & MBL Draft_Actual Planned | Pre_Alert_Actual | Pre Alert Planned | Cargo Arrival Notice Actual | Cargo Arrival Notice Planned | IGM Filing Actual | IGM Filing Planned | Line Invoice Received Actual | Line Invoice Received Planned | Operational Job Lock Actual | Billing to customer Actual | Billing to customer Planned | Line Invoice Payment Actual | Line Invoice Payment Planned | Delivery of Shipment Actual | Delivery of Shipment Planned | Remarks
SHP/SI/0166/25-26 | METRO BRANDS LIMITED | Komal Mhatre | Aniket Nair | 1x40HC | 35075601 | LCL | (NLRTM) Rotterdam | (INNSA) Nhava Sheva | 2025-07-21 | 2025-09-17 | 2025-09-16 | 2025-08-06 | 2025-08-07 | 2025-07-21 | 2025-07-21 | 2025-07-24 | 2025-07-24 | 2025-07-25 | 2025-07-25 | 2025-08-07 | 2025-08-07 | 2025-08-20 | 2025-08-20 | 2025-09-01 | 2025-09-01 | 2025-09-17 | 2025-09-17 |  |  | 2025-09-24 | 2025-09-18 | 2025-09-18 |  | 2025-09-22 | FINAL PRE-ALERT REC, LCL, ETA 19-SEP
SHP/SI/0167/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Sushmita Naik | 1x40HC | SNTG25055808 / YMJAN755282826 | FCL | (NLRTM) Rotterdam | (INNSA) Nhava Sheva | 2025-07-23 | 2025-09-15 | 2025-09-15 | 2025-07-29 | 2025-07-28 | 2025-07-22 | 2025-07-22 | 2025-07-18 | 2025-07-18 | 2025-07-24 | 2025-07-24 | 2025-07-29 | 2025-07-29 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-03 | 2025-09-15 | 2025-09-15 |  |  | 2025-09-25 | 2025-09-17 | 2025-09-16 |  | 2025-09-19 | ON-BOARD SENT// DOCS SENT TO ASHA // MANIFEST & FC SENT
SHP/SI/0170/25-26 | BLACK ROSE INDUSTRIES LIMITED | Jagan Pillai | Sushmita Naik |  | CMSTKNVS2507087 | LCL | (JPUKB) Kobe | (INNSA) Nhava Sheva | 2025-07-28 |  | 2025-09-22 | 2025-08-16 | 2025-08-16 | 2025-07-26 | 2025-07-26 | 2025-07-25 | 2025-07-25 | 2025-08-07 | 2025-08-07 | 2025-08-19 | 2025-08-19 | 2025-09-03 | 2025-09-02 | 2025-09-03 | 2025-10-02 |  | 2025-09-22 |  |  | 2025-09-23 |  | 2025-09-22 |  | 2025-09-23 | BOOKING DETAILS SENT, 10TH VESSEL DELAYED TO 16TH AUG vessel sailed/ reached hong kong 20.08.2025// CONNECTING VESSEL SENT OT CUSTOMER ETD 06.09.2025
SHP/SI/0191/25-26 | ASCENDIX MHE PRIVATE LIMITED | Anup Ramdas | Sushmita Naik | 1x40HC | DKK2508045 | FCL | (CNNGB) Ningbo | (INNSA) Nhava Sheva | 2025-08-04 |  | 2025-10-05 |  | 2025-09-19 | 2025-08-04 | 2025-08-04 | 2025-08-13 | 2025-08-10 | 2025-08-22 | 2025-08-22 |  | 2025-09-20 |  | 2025-10-01 |  | 2025-09-27 |  | 2025-10-06 |  |  | 2025-10-17 |  | 2025-10-06 |  | 2025-10-11 | BOOKING RECEIVED// VESSEL DELAYED FROM 28.08.2025 TO 05.09.2025 VESSEL DELAYED TO 13.09.2025 VESSEL DELAYED TO 18.09.2025 DUE TO PORT CONGESTION VESSEL DELAYED TO 19.09.2025
SHP/SI/0196/25-26 | VALTRIS SPECIALTY CHEMICALS INDIA PVT. LTD | Komal Mhatre | ABHILASH PATIL |  | AMIN3019285 | LCL | (USNYC) New York | (INNSA) Nhava Sheva | 2025-08-11 |  | 2025-10-11 | 2025-08-28 | 2025-08-28 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-11 | 2025-08-25 | 2025-08-22 | 2025-09-03 | 2025-08-30 |  | 2025-09-22 |  | 2025-09-23 |  | 2025-10-06 |  |  | 2025-10-13 |  | 2025-10-06 |  | 2025-10-10
SHP/SI/0197/25-26 | RISHI LASER LIMITED | Jagdish Shetty | Aniket Nair | 1x40HC | BSG25080364 / MAEU258684296 | FCL | (CNTSN) Tianjin | (INNSA) Nhava Sheva | 2025-08-11 | 2025-09-18 | 2025-09-24 | 2025-09-04 | 2025-09-03 | 2025-08-11 | 2025-08-08 | 2025-08-17 | 2025-08-15 | 2025-08-22 | 2025-08-20 | 2025-09-10 | 2025-09-05 | 2025-09-10 | 2025-09-15 | 2025-09-12 | 2025-09-15 | 2025-09-18 | 2025-09-25 |  |  | 2025-10-01 | 2025-09-18 | 2025-09-26 | 2025-09-18 | 2025-09-30 | ALERT: ROLL OVER AWAITING NOTICE/ AWAITING PICK-UP/ DRAFT BL PENDING-18TH AUG/ TELEX HBL RECEIVED MBL PENDING/ FC SENT
SHP/SI/0199/25-26 | RISHI LASER LIMITED | Jagdish Shetty | Aniket Nair | 1x40HC | AMIGL250369351A | LCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-08-11 | 2025-09-15 | 2025-09-15 | 2025-08-29 | 2025-08-27 | 2025-08-11 | 2025-08-08 | 2025-08-13 | 2025-08-12 | 2025-08-25 | 2025-08-20 | 2025-09-01 | 2025-09-01 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-15 | 2025-09-15 |  |  | 2025-09-22 | 2025-09-15 | 2025-09-15 |  | 2025-09-20 | DRAFT BL RECTIFICATION SENT 21ST AUG/ FC SENT/ TELEX HBL PENDING
SHP/SI/0204/25-26 | M/s PACKONE SOLUTIONS LLP | Ashritha Rai | Aniket Nair | 1x20GP | SGCJSHIP11017 / NAM7927401 | FCL | (USJLT) Shelton | (INGDH) Gandhinagar | 2025-08-14 |  | 2025-10-05 | 2025-08-26 | 2025-08-24 | 2025-08-14 | 2025-08-14 | 2025-08-17 | 2025-08-13 | 2025-08-21 | 2025-08-20 | 2025-08-29 | 2025-08-27 | 2025-09-05 | 2025-09-19 |  | 2025-09-22 |  | 2025-10-06 |  |  | 2025-10-07 |  | 2025-10-06 |  | 2025-10-07 | DRAFT RECEIVED/ DRAFT CONFIRMED/ FC SENT/ TELEX HBL RECEIVED MBL PENDING
SHP/SI/0206/25-26 | SACMI ENGINEERING INDIA PRIVATE LIMITED | Ankita Rout | Aniket Nair |  | SEIN25080108706 | LCL | (DEHAM) Hamburg | (INNSA) Nhava Sheva | 2025-08-14 |  | 2025-10-10 | 2025-08-26 | 2025-08-26 | 2025-08-14 | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-25 | 2025-08-21 | 2025-09-02 | 2025-08-26 | 2025-09-05 | 2025-09-18 |  | 2025-09-30 |  | 2025-10-13 |  |  | 2025-10-17 |  | 2025-10-13 |  | 2025-10-15 | AWAITING DRAFT BL/
SHP/SI/0208/25-26 | A W FABER CASTELL (INDIA) PRIVATE LIMITED | Ankita Rout | Aniket Nair | 1x20GP | HNSA2508X0316 / EMIVVNESHN203667 | FCL | (VNHPH) Haiphong | (INNSA) Nhava Sheva | 2025-08-14 |  | 2025-09-24 | 2025-08-25 | 2025-08-25 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-27 | 2025-08-26 | 2025-09-09 | 2025-09-08 |  | 2025-09-15 |  | 2025-09-25 |  |  | 2025-10-01 |  | 2025-09-26 |  | 2025-09-30
SHP/SI/0213/25-26 | Fotedar India Private Limited | Ashritha Rai | Aniket Nair | 1x40HC | SBKK00211306 / A15FX12242 | FCL | (THLCH) Laem Chabang | (INMUN) Mundra | 2025-08-20 | 2025-09-09 | 2025-09-07 | 2025-08-26 | 2025-08-26 | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-20 | 2025-08-25 | 2025-08-22 | 2025-08-28 | 2025-08-28 | 2025-09-02 | 2025-09-03 | 2025-09-01 | 2025-08-30 | 2025-09-10 | 2025-09-10 |  |  | 2025-09-20 | 2025-09-10 | 2025-09-10 |  | 2025-09-16 | CLERANCE INVOLVED/ TRANSPORTATION INVOLVED/ CFS INVOLVED/ FC SENT/ TELEX HBL MBL RECEIVED
SHP/SI/0215/25-26 | APAR INDUSTRIES LIMITED | Mithilesh Shetty | Aniket Nair |  | CTNVS2513807N | LCL | (CNDLC) Dalian | (INNSA) Nhava Sheva | 2025-08-21 |  | 2025-09-23 | 2025-09-01 | 2025-08-31 | 2025-08-21 | 2025-08-19 | 2025-08-21 | 2025-08-20 | 2025-08-26 | 2025-08-26 | 2025-09-04 | 2025-09-04 | 2025-09-02 | 2025-09-04 | 2025-09-09 | 2025-09-04 |  | 2025-09-23 |  |  | 2025-09-27 |  | 2025-09-24 |  | 2025-09-26 | PLANNING SET/ BOOKING SENT/ AWAITING DRAFT/ OBL SENT/ FC SENT/ TELEX HBL PENDING/ CAN PENDING
SHP/SI/0217/25-26 | CHOWGULE AND COMPANY PRIVATE LIMITED | Komal Mhatre | ABHILASH PATIL | 1x20GP | FGSH2508000214 / KMTCZHE0031143 | FCL | (CNZHE) Zhenjiang | (INNSA) Nhava Sheva | 2025-08-21 |  | 2025-09-21 | 2025-08-27 | 2025-09-02 | 2025-08-21 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-25 | 2025-08-25 | 2025-08-29 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-08-30 | 2025-09-08 |  | 2025-09-21 |  |  | 2025-09-27 |  | 2025-09-22 |  | 2025-09-27
SHP/SI/0218/25-26 | VOLTAS LIMITED | Deepak Palande | Aniket Nair |  | ICS2508276A | LCL | (CNSZX) Shenzhen | (INNSA) Nhava Sheva | 2025-08-21 | 2025-09-18 | 2025-09-16 | 2025-09-06 | 2025-09-06 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-25 | 2025-08-21 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-12 | 2025-09-10 | 2025-09-18 | 2025-09-16 |  |  | 2025-09-22 | 2025-09-18 | 2025-09-16 |  | 2025-09-22 | OBL RECEIVED/ FC SENT/ AWAITING CAN DETAILS
SHP/SI/0219/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Sushmita Naik | 1x40HC | FGSH2508000091 / ONEYSH5ACN027500 | FCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-08-22 | 2025-09-15 | 2025-09-15 | 2025-08-27 | 2025-08-26 | 2025-08-21 | 2025-08-21 | 2025-08-22 | 2025-08-22 | 2025-08-23 | 2025-08-23 | 2025-08-28 | 2025-08-27 | 2025-09-02 | 2025-09-05 | 2025-09-02 | 2025-09-05 | 2025-09-15 | 2025-09-15 |  |  | 2025-09-24 | 2025-09-15 | 2025-09-15 |  | 2025-09-20 | ON-BOARD BL SENT // DOCS SENT TO CLEARANCE TEAM FOR BOE // MANIFEST PENDING
SHP/SI/0220/25-26 | EPL LIMITED | Mithilesh Shetty | ABHILASH PATIL |  | ICS2508275A | LCL | (CNSZP) Shenzhen Pt | (INNSA) Nhava Sheva | 2025-08-23 |  | 2025-09-26 | 2025-09-15 | 2025-09-13 | 2025-08-23 | 2025-08-22 | 2025-08-23 | 2025-08-22 | 2025-09-04 | 2025-09-05 | 2025-09-15 | 2025-09-15 |  | 2025-09-20 | 2025-09-15 | 2025-09-12 |  | 2025-09-26 |  |  | 2025-09-30 |  | 2025-09-27 |  | 2025-09-30
SHP/SI/0221/25-26 | NASHER MILES PRIVATE LIMITED | Mithilesh Shetty | ABHILASH PATIL | 1x40HC | SZBS2507069 / ONEYNBOFA6729300 | FCL | (CNNGB) Ningbo | (INMAA) Chennai (ex Madras) | 2025-08-23 | 2025-09-14 | 2025-09-15 | 2025-08-29 | 2025-08-29 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-26 | 2025-08-25 | 2025-09-01 | 2025-09-01 | 2025-09-08 | 2025-09-10 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-16 |  |  | 2025-09-22 | 2025-09-15 | 2025-09-16 |  | 2025-09-22
SHP/SI/0222/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Sushmita Naik | 1x40HC | 12000825033 / MEDUKJ114595 | FCL | (NLRTM) Rotterdam | (INNSA) Nhava Sheva | 2025-08-25 |  | 2025-10-10 | 2025-08-30 | 2025-08-30 | 2025-08-22 | 2025-08-22 | 2025-08-19 | 2025-08-19 | 2025-08-22 | 2025-08-22 | 2025-09-02 | 2025-08-28 |  | 2025-09-22 |  | 2025-09-23 |  | 2025-10-10 |  |  | 2025-10-20 |  | 2025-10-13 |  | 2025-11-16 | PRE-ALERT SENT TO CUSTOMER//
SHP/SI/0223/25-26 | KITEX APPAREL PARKS LIMITED | Mithilesh Shetty | ABHILASH PATIL | 2x40HC | 93971627 | FCL | (USCHI) Chicago | (INNSA) Nhava Sheva | 2025-08-26 |  | 2025-10-20 |  | 2025-09-18 | 2025-08-26 | 2025-08-26 | 2025-09-03 | 2025-09-03 | 2025-09-11 | 2025-09-11 |  | 2025-09-19 |  | 2025-10-10 |  | 2025-10-10 |  | 2025-10-22 |  |  | 2025-10-28 |  | 2025-10-24 |  | 2025-10-28
SHP/SI/0224/25-26 | AYM SYNTEX LIMITED | Deepak Palande | Aniket Nair | 10x20GP | PCNVS25090065 / BLPLNGB2500045 | FCL | (CNNGB) Ningbo | (INNSA) Nhava Sheva | 2025-08-26 | 2025-09-18 | 2025-09-20 | 2025-09-06 | 2025-09-06 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-09-03 | 2025-08-28 | 2025-09-09 | 2025-09-08 | 2025-09-17 | 2025-09-15 | 2025-09-17 | 2025-09-15 |  | 2025-09-22 |  |  | 2025-09-26 |  | 2025-09-23 |  | 2025-09-25
SHP/SI/0225/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | KGNVS2509013 / A59FX08587 | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-08-28 | 2025-09-18 | 2025-09-18 | 2025-09-06 | 2025-09-06 | 2025-08-29 | 2025-08-28 | 2025-08-29 | 2025-08-29 | 2025-09-04 | 2025-09-04 | 2025-09-08 | 2025-09-08 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-09-19 |  |  | 2025-10-25 |  | 2025-09-19 |  | 2025-09-24 | IGM FILED/ FC SENT/
SHP/SI/0226/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | ISLI | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-08-28 | 2025-09-18 | 2025-09-18 | 2025-09-06 | 2025-09-06 | 2025-08-29 | 2025-08-28 | 2025-08-29 | 2025-08-28 | 2025-09-05 | 2025-09-04 | 2025-09-09 | 2025-09-08 | 2025-09-12 | 2025-09-11 | 2025-09-12 | 2025-09-12 |  | 2025-09-19 |  |  | 2025-09-24 |  | 2025-09-19 |  | 2025-09-22 | SAILING DONE/ FC SENT/ OBL SENT FOR RECTIFICATION
SHP/SI/0227/25-26 | Fotedar India Private Limited | Ashritha Rai | Aniket Nair | 1x20GP, 4x40HC | MSCU | FCL | (CNSHA) Shanghai | (INGIN) Gandhidham | 2025-08-28 |  | 2025-10-03 | 2025-09-15 | 2025-09-15 | 2025-08-28 | 2025-08-28 | 2025-09-04 | 2025-09-05 | 2025-09-09 | 2025-09-09 | 2025-09-16 | 2025-09-16 |  | 2025-09-22 |  | 2025-09-22 |  | 2025-10-03 |  |  | 2025-10-13 |  | 2025-10-06 |  | 2025-10-10 | Booking awaited
SHP/SI/0228/25-26 | DESAI ELECTRONICS PRIVATE LIMITED | Komal Mhatre | ABHILASH PATIL |  | JNSA2508040 | LCL | (KRPUS) Busan | (INNSA) Nhava Sheva | 2025-08-29 |  | 2025-09-30 | 2025-09-08 | 2025-09-07 | 2025-08-28 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-09-04 | 2025-09-03 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 |  | 2025-09-30 |  |  | 2025-10-05 |  | 2025-09-30 |  | 2025-10-05
SHP/SI/0229/25-26 | AYM SYNTEX LIMITED | Deepak Palande | ABHILASH PATIL |  | WJXG250919518N | LCL | (CNTSN) Tianjin | (INNSA) Nhava Sheva | 2025-08-29 |  | 2025-09-29 | 2025-09-08 | 2025-09-10 | 2025-08-29 | 2025-08-29 | 2025-08-30 | 2025-08-30 | 2025-09-03 | 2025-09-01 | 2025-09-08 | 2025-09-11 | 2025-09-15 | 2025-09-15 | 2025-09-12 | 2025-09-15 |  | 2025-09-29 |  |  | 2025-10-06 |  | 2025-09-29 |  | 2025-10-04
SHP/SI/0230/25-26 | WINEXT POLYTECH PRIVATE LIMITED | Siddharth Oberoi | ABHILASH PATIL | 2x40HC | HGCK250892654-1/ HGCK250892654-2 / MEDUW8555486 | FCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-09-01 |  | 2025-09-22 | 2025-09-02 | 2025-09-02 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-18 | 2025-09-18 | 2025-09-11 | 2025-09-12 |  | 2025-09-22 |  |  | 2025-09-25 |  | 2025-09-23 |  | 2025-09-24
SHP/SI/0231/25-26 | RISHI LASER LIMITED | Jagdish Shetty | Aniket Nair | 1x40HC | AMIGL250369363A | LCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-09-02 | 2025-09-15 | 2025-09-15 | 2025-08-27 | 2025-08-27 | 2025-09-06 | 2025-09-02 | 2025-08-13 | 2025-08-13 | 2025-08-25 | 2025-08-19 | 2025-09-04 | 2025-09-04 | 2025-09-09 | 2025-09-06 | 2025-09-09 | 2025-09-08 | 2025-09-15 | 2025-09-15 |  |  | 2025-09-23 | 2025-09-15 | 2025-09-15 |  | 2025-09-20 | JOB NO: SHP/SI/0198/25-26/ FC SENT/ TELEX HBL RECEIVED/ CAN SENT
SHP/SI/0232/25-26 | Grasper Global Private Limited | Mohit Shetty | Sushmita Naik | 1x20GP | DKK2509503 / 025F748387 | FCL | (CNSHK) Shekou | (INNSA) Nhava Sheva | 2025-09-02 |  | 2025-09-27 | 2025-09-12 | 2025-09-16 | 2025-09-02 | 2025-09-02 | 2025-09-03 | 2025-09-03 | 2025-09-04 | 2025-09-04 | 2025-09-12 | 2025-09-18 |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-29 |  |  | 2025-10-03 |  | 2025-09-30 |  | 2025-10-03 | BL DRAFT APPROVED, 10TH VESSEL DELAYED TO 15TH SEP DUE to port congestion vessel sailed 12.09.2025 on-board BL sent.
SHP/SI/0233/25-26 | YOKOHAMA INDIA PRIVATE LIMITED | AARON ALBERT RAJ | Sushmita Naik | 5x20GP | SJKT00212534 / SSLPLGTICAD0067 | FCL | (IDPLM) Palembang, Sumatra | (INNSA) Nhava Sheva | 2025-09-02 |  | 2025-09-22 | 2025-09-03 | 2025-09-05 | 2025-09-01 | 2025-09-01 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 |  | 2025-09-23 |  |  | 2025-09-30 |  | 2025-09-24 |  | 2025-09-26 | vessel sailed waiting for pre-alert docs
SHP/SI/0234/25-26 | YOKOHAMA INDIA PRIVATE LIMITED | AARON ALBERT RAJ | Sushmita Naik | 1x20GP | SJKT00212279 | FCL | (IDPLM) Palembang, Sumatra | (INNSA) Nhava Sheva | 2025-09-02 |  | 2025-09-22 | 2025-09-08 | 2025-09-05 | 2025-09-02 | 2025-09-01 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-08-26 | 2025-09-08 | 2025-09-06 | 2025-09-15 | 2025-09-20 | 2025-09-16 | 2025-09-15 |  | 2025-09-23 |  |  | 2025-09-30 |  | 2025-09-25 |  | 2025-09-27 | ON-BOARD BL SENT// FC SENT
SHP/SI/0235/25-26 | YOKOHAMA INDIA PRIVATE LIMITED | AARON ALBERT RAJ | Sushmita Naik | 5x20GP | SJKT00212288 | FCL | (IDPLM) Palembang, Sumatra | (INNSA) Nhava Sheva | 2025-09-02 |  | 2025-09-25 | 2025-09-03 | 2025-09-04 | 2025-09-02 | 2025-09-01 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 |  | 2025-09-26 |  |  | 2025-10-01 |  | 2025-09-27 |  | 2025-09-30 | VESSEL SAILED PRE-ALERT SENT// FC SENT
SHP/SI/0236/25-26 | NASHER MILES PRIVATE LIMITED | Mithilesh Shetty | ABHILASH PATIL | 1x40HC | YSNBF25091612 / SLSNBZ03883 | FCL | (CNNGB) Ningbo | (INMAA) Chennai (ex Madras) | 2025-09-03 |  | 2025-09-19 | 2025-09-08 | 2025-09-07 | 2025-09-02 | 2025-09-02 | 2025-09-03 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-08 | 2025-09-12 | 2025-09-12 | 2025-09-10 | 2025-09-12 |  | 2025-09-19 |  |  | 2025-10-03 |  | 2025-09-20 |  | 2025-09-27
SHP/SI/0237/25-26 | Azelis India Pvt Ltd | Anup Ramdas | Sushmita Naik | 1x40HC |  | FCL | (USZFT) Illinois City | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-10-27 |  | 2025-09-19 | 2025-09-04 | 2025-09-03 | 2025-09-04 | 2025-09-03 | 2025-09-15 | 2025-09-16 |  | 2025-09-22 |  | 2025-10-15 |  | 2025-10-25 |  | 2025-10-29 |  |  | 2025-10-31 |  | 2025-10-30 |  | 2025-10-31
SHP/SI/0238/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | ISLI | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-09-25 | 2025-09-14 | 2025-09-14 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-12 | 2025-09-11 | 2025-09-15 | 2025-09-15 |  | 2025-09-22 |  | 2025-09-19 |  | 2025-09-23 |  |  | 2025-09-29 |  | 2025-09-23 |  | 2025-09-29
SHP/SI/0239/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | ISLI | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-09-25 | 2025-09-14 | 2025-09-14 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-15 | 2025-09-15 |  | 2025-10-01 |  | 2025-09-19 |  | 2025-09-26 |  |  | 2025-10-03 |  | 2025-09-29 |  | 2025-10-02 | DRAFT CONFIRMATION PENDING/
SHP/SI/0240/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | ISLI | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-09-25 | 2025-09-14 | 2025-09-14 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-10 | 2025-09-15 | 2025-09-17 |  | 2025-10-03 |  | 2025-09-19 |  | 2025-09-23 |  |  | 2025-09-30 |  | 2025-09-23 |  | 2025-09-29 | DRAFT CONFIRMATION AWAITING/
SHP/SI/0241/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | ISLI | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-09-25 | 2025-09-14 | 2025-09-14 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-12 | 2025-09-11 | 2025-09-15 | 2025-09-17 |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-24 |  |  | 2025-10-02 |  | 2025-09-25 |  | 2025-10-01 | AWAITING REVISED DRAFT BL
SHP/SI/0242/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC |  | FCL | (VNSGN) Ho Chi Minh City | (INCCU) Kolkata (ex Calcutta) | 2025-09-03 |  | 2025-10-04 | 2025-09-14 | 2025-09-14 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-10 | 2025-09-11 | 2025-09-15 | 2025-09-17 |  | 2025-10-01 |  | 2025-09-22 |  | 2025-10-06 |  |  | 2025-10-13 |  | 2025-10-07 |  | 2025-10-10 | AWAITING SAILING
SHP/SI/0243/25-26 | SACMI ENGINEERING INDIA PRIVATE LIMITED | Ankita Rout | Aniket Nair | 1x20GP, 1x40HC | DKK2509505 / EMIVHNGHKG207686 | FCL | (CNNSA) Nansha | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-09-24 | 2025-09-06 | 2025-09-06 | 2025-09-03 | 2025-09-03 | 2025-08-29 | 2025-08-29 | 2025-09-04 | 2025-09-02 | 2025-09-08 | 2025-09-10 |  | 2025-09-19 |  | 2025-09-19 |  | 2025-09-24 |  |  | 2025-09-27 |  | 2025-09-25 |  | 2025-09-26 | DRAFT CONFIRMED/ SAILING DONE/ TELEX MBL PENDING/ FC SENT/
SHP/SI/0245/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Sushmita Naik | 1x40HC | 12000825030 / MSCU | FCL | (NLRTM) Rotterdam | (INNSA) Nhava Sheva | 2025-09-03 |  | 2025-10-10 | 2025-09-02 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-01 | 2025-09-01 | 2025-09-04 | 2025-09-02 |  | 2025-10-01 | 2025-09-18 | 2025-10-01 |  | 2025-10-11 |  |  | 2025-10-14 |  | 2025-10-13 |  | 2025-10-14
SHP/SI/0247/25-26 | RANK LOGISTICS PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x20GP |  | FCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-09-05 |  | 2025-10-02 | 2025-09-16 | 2025-09-16 | 2025-09-05 | 2025-09-05 | 2025-09-04 | 2025-09-04 | 2025-09-09 | 2025-09-08 | 2025-09-18 | 2025-09-18 |  | 2025-09-24 |  | 2025-09-19 |  | 2025-10-03 |  |  | 2025-10-07 |  | 2025-10-03 |  | 2025-10-06 | AWAITING REVISED DRAFT BL
SHP/SI/0248/25-26 | CH101 MARKET PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | MSCU | FCL | (CNNGB) Ningbo | (INMUN) Mundra | 2025-09-08 |  | 2025-10-03 |  | 2025-09-20 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-11 |  | 2025-09-22 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-03 |  |  | 2025-10-10 |  | 2025-10-06 |  | 2025-10-09
SHP/SI/0249/25-26 | CH101 MARKET PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | QDWJ25091157 | LCL | (CNTAO) Qingdao | (INNSA) Nhava Sheva | 2025-09-09 |  | 2025-09-30 | 2025-09-11 | 2025-09-11 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-12 | 2025-09-15 |  | 2025-09-22 |  | 2025-09-22 |  | 2025-09-30 |  |  | 2025-10-06 |  | 2025-09-30 |  | 2025-10-03 | AWAITING SAILING CONFIRMATION
SHP/SI/0250/25-26 | Fotedar India Private Limited | Ashritha Rai | Aniket Nair | 1x40HC |  | FCL | (THLCH) Laem Chabang | (INNSA) Nhava Sheva | 2025-09-09 |  | 2025-09-25 | 2025-09-16 | 2025-09-16 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-12 | 2025-09-12 | 2025-09-18 | 2025-09-18 |  | 2025-09-22 |  | 2025-09-19 |  | 2025-09-26 |  |  | 2025-10-06 |  | 2025-10-01 |  | 2025-10-03 | DRAFT CONFIRMED
SHP/SI/0251/25-26 | A W FABER CASTELL (INDIA) PRIVATE LIMITED | Ankita Rout | Aniket Nair | 1x20GP | MSCU | FCL | (CNDLC) Dalian | (INNSA) Nhava Sheva | 2025-09-09 |  | 2025-10-30 |  | 2025-09-19 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2025-09-22 |  | 2025-09-26 |  | 2025-09-24 |  | 2025-10-29 |  |  | 2025-10-03 |  | 2025-10-29 |  | 2025-10-03 | DRAFT CONFIRMED/ AWAITING SAILING
SHP/SI/0252/25-26 | KALMAR INDIA PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 4x40HC | ISLI | FCL | (MYPKG) Port Klang (Pelabuhan Klang) | (INNSA) Nhava Sheva | 2025-09-09 |  | 2025-09-26 |  | 2025-09-19 | 2025-09-09 | 2025-09-09 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-15 |  | 2025-09-23 |  | 2025-09-22 |  | 2025-09-19 |  | 2025-09-26 |  |  | 2025-09-30 |  | 2025-09-26 |  | 2025-09-30
SHP/SI/0253/25-26 | MARSHALLS ENTERPRISE INDIA PVT LTD | Mithilesh Shetty | ABHILASH PATIL |  | EU16SG252587 | LCL | (CNTSN) Tianjin | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-05 |  | 2025-09-21 | 2025-09-10 | 2025-09-09 | 2025-09-10 | 2025-09-10 | 2025-09-16 | 2025-09-16 |  | 2025-09-23 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-06 |  |  | 2025-10-14 |  | 2025-10-07 |  | 2025-10-14
SHP/SI/0254/25-26 | WINEXT POLYTECH PRIVATE LIMITED | Siddharth Oberoi | ABHILASH PATIL | 1x40HC | DKK2509108 / MSCU | FCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-04 | 2025-09-17 | 2025-09-17 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-15 | 2025-09-13 | 2025-09-18 | 2025-09-18 |  | 2025-09-30 |  | 2025-09-19 |  | 2025-10-04 |  |  | 2025-10-15 |  | 2025-10-06 |  | 2025-10-14
SHP/SI/0255/25-26 | RISHABH INDUSTRIES | Ashritha Rai | Aniket Nair |  | GFCP | LCL | (CNSZX) Shenzhen | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-03 |  | 2025-09-19 | 2025-09-10 | 2025-09-09 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-08 |  | 2025-09-20 |  | 2025-09-25 |  | 2025-09-24 |  | 2025-10-04 |  |  | 2025-10-10 |  | 2025-10-06 |  | 2025-10-09 | DRAFT CONFIRMED/ ETD: 13TH SEP
SHP/SI/0256/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-03 |  | 2025-09-20 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-18 | 2025-09-17 |  | 2025-09-22 |  | 2025-09-25 |  | 2025-09-25 |  | 2025-10-06 |  |  | 2025-10-11 |  | 2025-10-06 |  | 2025-10-09 | STUFFING UNDERWAY
SHP/SI/0257/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-03 |  | 2025-09-20 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-18 | 2025-09-17 |  | 2025-09-22 |  | 2025-09-25 |  | 2025-09-25 |  | 2025-10-06 |  |  | 2025-10-10 |  | 2025-10-06 |  | 2025-10-09
SHP/SI/0258/25-26 | GRAUER AND WEIL (INDIA) LIMITED | Deepak Palande | Aniket Nair |  | GFCP | LCL | (CNSHA) Shanghai | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-16 |  | 2025-09-25 | 2025-09-10 | 2025-09-10 | 2025-09-18 | 2025-09-17 |  | 2025-09-22 |  | 2025-09-26 |  | 2025-09-30 |  | 2025-09-30 |  | 2025-10-16 |  |  | 2025-10-22 |  | 2025-10-17 |  | 2025-10-21 | booking awated from shipper
SHP/SI/0259/25-26 | RISHABH INDUSTRIES | Ashritha Rai | Aniket Nair |  | GFCP | LCL | (CNNGB) Ningbo | (INNSA) Nhava Sheva | 2025-09-10 |  | 2025-10-06 | 2025-09-16 | 2025-09-17 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-12 | 2025-09-11 |  | 2025-09-19 |  | 2025-09-25 |  | 2025-09-25 |  | 2025-10-06 |  |  | 2025-10-13 |  | 2025-10-06 |  | 2025-10-10 | DRAFT CONFIRMED/ OBL PENDING
SHP/SI/0260/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Sushmita Naik | 1x20GP | 12000925011 / MSCU | FCL | (NLRTM) Rotterdam | (INNSA) Nhava Sheva | 2025-09-12 |  | 2025-10-25 | 2025-09-10 | 2025-09-10 | 2025-09-12 | 2025-09-05 | 2025-09-04 | 2025-09-10 | 2025-09-05 | 2025-09-08 | 2025-09-12 | 2025-09-12 |  | 2025-10-08 |  | 2025-10-17 |  | 2025-10-25 |  |  | 2025-11-01 |  | 2025-10-27 |  | 2025-10-29 | ON-BOARD BL SENT
SHP/SI/0261/25-26 | FOUR ACES FASHION HOUSE PVT. LTD. | Jagdish Bhandari | ABHILASH PATIL | 1x20GP | DKK2509512 / EGLV149506538087 | FCL | (CNDCB) Da Chan Bay | (INNSA) Nhava Sheva | 2025-09-16 |  | 2025-10-08 | 2025-09-16 | 2025-09-16 | 2025-09-15 | 2025-09-13 | 2025-09-15 | 2025-09-14 | 2025-09-16 | 2025-09-16 |  | 2025-09-18 |  | 2025-10-03 |  | 2025-09-29 |  | 2025-10-09 |  |  | 2025-10-16 |  | 2025-10-10 |  | 2025-10-16
SHP/SI/0262/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-16 |  | 2025-10-11 |  | 2025-09-27 | 2025-09-16 | 2025-09-09 | 2025-09-18 | 2025-09-17 |  | 2025-09-24 |  | 2025-09-30 |  | 2025-10-01 |  | 2025-10-01 |  | 2025-10-13 |  |  | 2025-10-20 |  | 2025-10-14 |  | 2025-10-18
SHP/SI/0263/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-16 |  | 2025-10-11 |  | 2025-09-27 | 2025-09-16 | 2025-09-16 | 2025-09-18 | 2025-09-17 |  | 2025-09-24 |  | 2025-09-30 |  | 2025-10-01 |  | 2025-10-01 |  | 2025-10-13 |  |  | 2025-10-20 |  | 2025-10-14 |  | 2025-10-18
SHP/SI/0264/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-16 |  | 2025-10-11 |  | 2025-09-27 | 2025-09-16 | 2025-09-16 | 2025-09-18 | 2025-09-17 |  | 2025-09-24 |  | 2025-09-30 |  | 2025-10-01 |  | 2025-10-01 |  | 2025-10-13 |  |  | 2025-10-20 |  | 2025-10-14 |  | 2025-10-18
SHP/SI/0265/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-16 |  | 2025-10-11 |  | 2025-09-27 | 2025-09-16 | 2025-09-18 | 2025-09-18 | 2025-09-17 |  | 2025-09-24 |  | 2025-09-30 |  | 2025-10-01 |  | 2025-10-01 |  | 2025-10-13 |  |  | 2025-10-20 |  | 2025-10-14 |  | 2025-10-18
SHP/SI/0266/25-26 | MAESTRO TRADEX PRIVATE LIMITED | Ashritha Rai | Aniket Nair | 1x40HC | EGLV | FCL | (VNVIC) Ho Chi Minh, VICT | (INNSA) Nhava Sheva | 2025-09-16 |  | 2025-10-11 |  | 2025-09-27 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 |  | 2025-09-24 |  | 2025-09-30 |  | 2025-10-01 |  | 2025-10-01 |  | 2025-10-13 |  |  | 2025-10-20 |  | 2025-10-14 |  | 2025-10-18 | DRAFT PENDING
SHP/SI/0267/25-26 | LION RUBBER INDUSTRIES PRIVATE LIMITED | Jagdish Shetty | Aniket Nair | 1x40OT |  | FCL | (CNTAO) Qingdao | (INNSA) Nhava Sheva | 2025-09-17 |  | 2025-10-10 |  | 2025-09-25 | 2025-09-17 | 2025-09-12 | 2025-09-17 | 2025-09-17 |  | 2025-09-19 |  | 2025-09-27 |  | 2025-10-03 |  | 2025-09-27 |  | 2025-10-09 |  |  |  |  | 2025-10-13 |  | 2025-10-14
SHP/SI/0268/25-26 | REICHHOLD INDIA PRIVATE LIMITED | Santosh Shetty | ABHILASH PATIL | 4x20GP | PUSNSA1722123846 | FCL | (KRPUS) Busan | (INNSA) Nhava Sheva | 2025-09-17 |  | 2025-10-09 |  | 2025-09-19 | 2025-09-15 | 2025-09-13 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 |  | 2025-09-20 |  | 2025-10-02 |  | 2025-09-30 |  | 2025-10-10 |  |  | 2025-10-17 |  | 2025-10-10 |  | 2025-10-17
SHP/SI/0269/25-26 | NASHER MILES PRIVATE LIMITED | Mithilesh Shetty | ABHILASH PATIL | 1x40HC | EGLV | FCL | (CNSHA) Shanghai | (INMAA) Chennai (ex Madras) | 2025-09-17 |  | 2025-10-10 |  | 2025-09-21 | 2025-09-13 | 2025-09-13 | 2025-09-15 | 2025-09-15 | 2025-09-17 | 2025-09-17 |  | 2025-09-23 |  | 2025-10-04 |  | 2025-09-25 |  | 2025-10-11 |  |  | 2025-10-17 |  | 2025-10-11 |  | 2025-10-16
SHP/SI/0270/25-26 | NASHER MILES PRIVATE LIMITED | Mithilesh Shetty | ABHILASH PATIL | 1x40HC | YSNBF25092997 / EGLV143571384375 | FCL | (CNNGB) Ningbo | (INMAA) Chennai (ex Madras) | 2025-09-17 |  | 2025-10-11 |  | 2025-09-21 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 |  | 2025-09-23 |  | 2025-10-04 |  | 2025-09-30 |  | 2025-10-13 |  |  | 2025-10-20 |  | 2025-10-13 |  | 2025-10-19
SHP/SI/0271/25-26 | DCC PRINT VISION LLP | Anup Ramdas | Sushmita Naik | 1x40HC |  | FCL | (CNZUH) Zhuhai | (INNSA) Nhava Sheva | 2025-09-17 |  | 2025-09-28 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-10 | 2025-09-10 | 2025-09-08 | 2025-09-10 | 2025-09-08 | 2025-09-15 | 2025-09-15 |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-29 |  |  | 2025-10-04 |  | 2025-09-29 |  | 2025-10-02
SHP/SI/0272/25-26 | NASHER MILES PRIVATE LIMITED | Mithilesh Shetty | ABHILASH PATIL | 1x40HC | YSNBF25093642 / SLSNBZ04039 | FCL | (CNNGB) Ningbo | (INMAA) Chennai (ex Madras) | 2025-09-18 |  | 2025-10-08 |  | 2025-09-24 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-17 | 2025-09-17 |  | 2025-09-26 |  | 2025-10-04 |  | 2025-09-30 |  | 2025-10-09 |  |  | 2025-10-15 |  | 2025-10-09 |  | 2025-10-14